## Sheet1
Sno | Tasks | Developer | Date of Completion | Status | Reviewer
1 | Create MDM projects for Entity attribte masters. 1. UI 2. Service 3. Business Layer 4. Data 5. Data Access Layer | Ujjval | 5th May
2 | Create New MDM DB and add the tables provided in the assignment. Also add some master data into the table. | Pragya | 5th May
3 | Design Inner Screen to add/modify master attributes | Ujjval | 6th May
4 | Create Views for different Master Attributes. | Pragya | 6th May
5 | Create SP to store Master Attributes. We will be having wrapper SP calls from application that will contain separate SP callings based on their inputs. Following are the SPs need to be created : 1. A SP for Entity’s Master Attributes. 2. A SP for Contact/Address Master Attributes. 3. A SP for Business Client/Transactional Client/Reporting Deliver & Processing Groups. 4. A SP for Service Provider | Pragya | 7th - 8th May
6 | *Discussion of screen created, reviewed with team memebers and work on reviewed comments(if any). *Create DTO class for Entity Attribute Master. | Ujjval | 7th May
7 | Screen : Enable/Disable input control based on control navigation. Screen/BLL/Data access : Create method to fill combo for attribute master | Ujjval | 8th May
8 | Screen : Bind Combo for attribute values in screen based on attributes master. | Ujjval | 11th May